## Inspection
image | captured_at | location | component | condition | severity | observation | recommendation
DJI_20260317154903_0015_V.JPG | 2026-03-17T15:49:03 |  | Powerline-side structural connection | painted welded bracket and stiffener visible with no obvious damage in this view | ok | The image shows a welded steel bracket/stiffener connection on the powerline side. Weld beads and surrounding painted surfaces appear intact, with no clearly visible cracking, deformation, or significant corrosion in the photographed area. | Continue the inspection from the powerline side and monitor this connection in closer views for any coating damage, weld cracking, or corrosion not visible in this image.
DJI_20260317154939_0016_V.JPG | 2026-03-17T15:49:39 |  | rail joint | visible gap/step at rail joint | major | The photo shows a rail joint with a noticeable uneven transition and open gap beneath the rail end/support area. The operator commentary indicates this location is between pillars 10-11 and 12-13 and mentions multiple photos at the same issue location. | Carry out a closer inspection of the rail joint alignment and support condition at the referenced pillar spans. Check for looseness, settlement, wear, and dimensional compliance, and repair or realign the joint/support as needed.
DJI_20260317154942_0017_V.JPG | 2026-03-17T15:49:42 |  | Bridge girder/web section between pillars 12-13 | Painted steel surface appears intact with minor irregularity along the upper flange/edge | minor | The photographed girder section shows a generally uniform dark coating with no clearly visible heavy corrosion, cracking, or deformation. Along the top edge/flange, there are small surface irregularities consistent with uneven coating or minor localized deterioration. | Monitor this area in the related photos for continuity of the top-edge condition and touch up or further inspect the upper flange/edge if coating breakdown or corrosion is confirmed on closer examination.
DJI_20260317155033_0018_V.JPG | 2026-03-17T15:50:33 |  | pillar / beam surface on right side between pillars 14-13 | small dent/mark | minor | The operator reports a small dent/mark on the right side between pillars 14-13. In the photo, the steel surface appears intact overall, with a localized visible mark and surface debris/discoloration along the edge. | Clean the area and inspect the marked spot at close range to confirm the extent of the dent/mark and verify that there is no associated cracking, deformation, or coating damage requiring repair.
DJI_20260317155335_0019_V.JPG | 2026-03-17T15:53:35 |  | girder top flange edge | coating deterioration | minor | The image shows localized paint breakdown and surface corrosion/discoloration along the top flange edge, with worn and peeling coating visible across the upper edge. No clear cracking or significant deformation is visible in this view. | Clean and prepare the affected areas, repair the coating system, and monitor the edge for any progression of corrosion during the next inspection.
DJI_20260317155339_0020_V.JPG | 2026-03-17T15:53:39 |  | steel beam top flange/edge coating | coating deterioration visible | minor | The photo shows the top edge of a painted steel member with a dark exposed strip along the upper seam/edge and multiple areas of paint peeling or flaking on the horizontal face. No clear structural deformation or active heavy corrosion is visible in this image. | Clean and inspect the affected edge and seam more closely for underlying corrosion, then repair the coating system where paint loss and exposed material are present.
DJI_20260317155350_0021_V.JPG | 2026-03-17T15:53:50 |  | girder underside weld area | localized coating damage/discoloration at weld termination | minor | Underside of the steel girder is visible with a vertical weld seam at center. There is a small darkened area and minor coating irregularity around the lower end of the weld, while the surrounding painted surfaces appear generally intact. No clear crack or major deformation is visible in this image. | Clean and closely inspect the weld termination and surrounding coating during the next maintenance access. Touch up the coating if damage is confirmed and monitor for any progression, corrosion, or cracking.
DJI_20260317155442_0022_V.JPG | 2026-03-17T15:54:42 |  | girder/web plate and welded attachment | paint wear and localized coating damage visible | minor | The image shows a steel girder/web plate with a small welded attachment at the center. There are scattered paint chips and surface abrasion around the weld area and a broader rubbed/worn patch on the lower painted surface. No obvious cracking, deformation, or heavy corrosion is visible in this view. | Clean and monitor the affected area, and repair the coating where paint has chipped or worn through to maintain corrosion protection. Reinspect the weld attachment during the next close inspection for any developing cracks or rust staining.
DJI_20260317155608_0023_V.JPG | 2026-03-17T15:56:08 |  | runway rail and supporting beam surface | surface contamination and coating wear visible | minor | The photo shows a runway rail mounted on a beam with accumulated dust/debris and scattered yellow residue on the top surface. Dark coating on and around the rail appears worn or uneven in places, with small exposed patches visible on the beam top. No obvious cracking, breakage, or rail misalignment is visible in this image. | Clean the beam top and rail area to remove debris/residue and monitor the worn coating areas. Reinspect after cleaning to confirm whether any underlying corrosion or damage is present.
DJI_20260317155618_0024_V.JPG | 2026-03-17T15:56:18 |  | beam top flange / rail seat | surface coating wear and debris present | minor | The photo shows a steel beam top surface with a narrow strip/seat along the center. There are localized areas of paint/coating loss on the top surface, light dust/debris accumulation, and dark staining along the strip. No obvious crack, deformation, or severe corrosion is visible in this image. | Clean the surface and monitor the worn coating and staining during the next inspection. Touch up exposed coating as needed to prevent corrosion if this is a painted surface.
DJI_20260317155901_0025_V.JPG | 2026-03-17T15:59:01 |  | beam flange/welded joint | paint wear and possible surface moisture/staining visible at welded seam | minor | Close-up of a painted steel beam flange with a small welded joint. The top edge shows light coating wear/rust staining, and there is a darker wet-looking or stained area on the lower horizontal surface beneath the weld. No clear fracture or major deformation is visible in this image. | Clean and inspect the welded seam and surrounding flange at closer range to confirm whether the dark area is moisture, staining, or coating breakdown, and touch up coating where worn.
DJI_20260317160018_0026_V.JPG | 2026-03-17T16:00:18 |  | beam surface/coating | localized paint wear and coating irregularity visible | minor | The image shows a painted steel beam or rail surface with a small area of coating loss/scuffing on the lower horizontal face and uneven paint buildup along the upper edge. No crack, deformation, or active corrosion is clearly visible in this view. | Clean the area and touch up the coating as needed, then monitor during the next inspection for any progression or signs of corrosion.
DJI_20260317160131_0027_V.JPG | 2026-03-17T16:01:31 |  | girder web-to-flange welded joint | painted welded connection visible; no obvious cracking or deformation evident in the image | ok | The image shows a vertical weld joining the web to the flange inside the girder. The weld bead is continuous and coated with paint. No clear cracks, missing weld sections, or visible deformation are apparent from this view. | Continue routine inspection and monitor the weld during future checks for any paint breakdown, cracking, or corrosion that may become visible.
DJI_20260317160146_0028_V.JPG | 2026-03-17T16:01:46 |  | girder rail/support weld area | painted structural steel with visible welds and rail contact surface | unknown | The image shows a crane girder rail or track support area with coated steel surfaces. A transverse weld beneath the rail/support flange is visible, along with a small paint drip/run at the weld location. No clear cracking, deformation, or obvious missing parts are visible in this view. | Monitor this area during routine inspection and, if required, obtain closer views of the weld and rail fastening/support details to confirm condition and coating integrity.
DJI_20260317160214_0029_V.JPG | 2026-03-17T16:02:14 |  | runway rail and beam top flange | minor surface wear visible | minor | The image shows the runway rail mounted on the beam top flange. The rail running surface appears generally straight, with small localized paint loss and minor surface irregularities or residue along the rail seat/top flange area. No obvious crack, major deformation, or severe corrosion is visible in this view. | Clean and monitor the rail seat/top flange area during routine inspection, and verify the minor surface wear does not progress to corrosion, looseness, or rail misalignment.
DJI_20260317160219_0030_V.JPG | 2026-03-17T16:02:19 |  | bridge girder / runway beam surface | painted steel surface visible with minor coating irregularity | minor | The image shows painted steel beam members in the foreground. Along the upper edge of the nearest beam, the coating appears uneven with small localized patches or scuffs. No obvious crack, deformation, or active corrosion is visible in this view. | Monitor the affected coated areas during routine inspection and touch up the paint if required to maintain corrosion protection. Obtain closer images if a more detailed condition assessment of the beam edge is needed.
DJI_20260317160404_0031_V.JPG | 2026-03-17T16:04:04 |  | welded beam joint | visible surface crack/discontinuity at weld area | major | A welded joint on the beam shows a distinct vertical crack or discontinuity extending from the upper surface down into the weld area at the center of the image. Surrounding coating appears intact overall, with minor surface staining/discoloration. | Perform close-up inspection of the joint and weld, including cleaning and suitable NDT to confirm the extent of cracking. Assess structural significance and repair the weld/joint as required before continued service.
DJI_20260317160411_0032_V.JPG | 2026-03-17T16:04:11 |  | girder weld joint | surface discontinuity visible | major | Close-up of a welded joint on a steel member shows a visible crack-like discontinuity at the center of the weld/bead area, with dark heat-affected discoloration around the joint. No other crane components are visible in this image. | Perform a detailed inspection of the weld joint, including close visual and appropriate NDT, to confirm the extent of the discontinuity and assess structural significance. Repair the weld as required and re-inspect after repair.
DJI_20260317160417_0033_V.JPG | 2026-03-17T16:04:17 |  | welded beam/flange connection | visible surface crack at weld area | major | The image shows a welded steel connection with a distinct vertical crack/discontinuity crossing the flange edge and extending into the weld bead at the center of the joint. No operator commentary is available, and the photo provides only a close-up view of this localized area. | Carry out a detailed inspection of the weld and adjacent base metal, including crack extent verification with appropriate NDT, and assess the connection for repair by qualified personnel before returning it to service.
DJI_20260317160420_0034_V.JPG | 2026-03-17T16:04:20 |  | welded joint on beam/flange | surface crack visible at weld area | major | A localized crack is visible running vertically from the upper edge into the welded area at the center of the image. The surrounding weld bead appears uneven, with no clear evidence in the photo of complete separation. | Perform a close-up inspection of the weld/joint, clean the area, and verify crack extent with appropriate NDT. Assess structural significance and repair the weld if confirmed.
DJI_20260317160449_0035_V.JPG | 2026-03-17T16:04:49 |  | girder/beam surface and upper seam | surface irregularity visible | unknown | The image shows painted steel girder or beam sections. Along the upper seam/edge of the central member, there is a dark, uneven line with localized rough buildup or irregularity visible over part of the length. No clear crack, deformation, or severe corrosion is definitively visible from this view. | Inspect this seam/edge at closer range to determine whether the visible irregularity is sealant, weld/paint buildup, debris, or coating damage, and clean or repair as needed based on the close-up inspection.

## Summary
field | value
site | R-tai Kylkkihalli-demoinspektiini
date | 2026-03-17
overall_severity | major
inspection_overview | Drone inspection started from the powerline side, right side, covering pillars 10 to 15. Transcript references multiple images taken at pillar spans including 10-11, 12-13, 13-14, 14-13, and 13-12.
notable_transcript_points | Powerline side inspected first; operator noted multiple rail-related photos at several pillar spans and mentioned a small defect/mark between pillars 14-13. Some locations were described as looking good.
major_findings_summary | Major findings include a rail joint with visible gap/step and multiple welded joint locations with visible crack/discontinuity at the weld area.
source_transcript | R-tai Kylkkihalli-demoinspektiini on käynnistetty droneen kanssa, aloittamalla Powerline-puolelta, oikealta puolelta, aloittamalla Pillar 10 ja Pillar 15. Pillar 10. Yksi kuva reilustruktuuria. Pillar 10-11. Kaksi kuvaa reilun väestön markkinaa. Yksi kuva siitä, joten kolme kuvaa reilun kohdalla. Pillar 12-13. Kaksi kuvaa reilun väestön markkinaa. Samassa vaiheessa yksi kuvaa reilun väestön markkinaa. Pillar 13. Yksi kuva reilun väestön markkinaa. Yksi kuva. Pillar 13-14. Näyttää olevan reilun väestön markkinaan jälkeen. Kaksi kuvaa reilun väestön markkinaa. Katsotaan nyt puolet, joilla ei ole voimaa. Aloitetaan taas oikeasta puolelta. Tällä puolella on reilun 15-10. Pillar 14-13. Reilun väestön markkinaan on pieni jälkeen. Yksi kuva. Pillar 13-12. Reilun väestön markkinaan on pieni jälkeen. Yksi kuva. Pillar 13-12. Reilun väestön markkinaan. Yksi kuva. Näyttää hyvältä. Samassa vaiheessa reilun väestön markkinaan. Yksi kuva. Näyttää hyvältä. Pillar 13-12. Reilun väestön markkinaan. Kaksi kuvaa siitä. Pillar 10-11. Reilun väestön markkinaan. Yksi. Kaksi kuvaa siitä. Pillar 10-11. Reilun väestön markkinaan. Yksi kuva siitä.